## Project Overview
Counter Cultures × Untold Works — Project Roadmap
Created: April 3, 2026 ¦ Status: Active ¦ Last Updated: April 03, 2026
Workstream | Owner | Tasks | Status | Target Start | Target Complete | Notes
1. Platform Setup | Untold Works + Roger | 9 | Not Started | Week 1 | Week 2 | Google Workspace, Stripe verify, domain, Odoo extract
2. Catalog & Content | Untold Works + Roger | 20 | In Progress | Week 1 | Week 4 | 491 products, images, copy, brand pages
3. Operations Build | Untold Works | 13 | Not Started | Week 3 | Week 5 | CRM wiring, order tracking, finance dashboard, AI chatbot
4. Marketing Engine | Untold Works | 10 | Not Started | Week 5 | Week 8 | SEO, AEO, social, blog, newsletter, trade program
5. Launch & Handoff | Untold Works + Roger | 7 | Not Started | Week 6 | Week 8 | Training, go-live checklist, monitoring

## Tasks
Task | Workstream | Owner | Priority | Status | Deck Slide | Dependencies | Target Week | Notes
Get Odoo URL from Roger | Platform Setup | Roger | Critical | Not Started | Close | — | Week 1 | Need to extract existing customer data, sales history, invoices
Extract Odoo data → Google Sheets CRM | Platform Setup | Untold Works | Critical | Not Started | Roadmap | Odoo URL | Week 1 | Contacts, sales history, invoices → Sheets tabs
Verify Stripe Mexico connection | Platform Setup | Untold Works | Critical | Not Started | Close | — | Week 1 | Stripe already connected per Joshua — verify live + bank payout
Connect Google Workspace | Platform Setup | Roger | Critical | Not Started | Close | — | Week 1 | Service account needs access to Roger's Workspace
Confirm contact details (phone + email domain) | Platform Setup | Roger | High | Not Started | Close | — | Week 1 | Phone is placeholder; email discrepancy .mx vs .com.mx
Domain decision — point countercultures.com.mx to Netlify | Platform Setup | Roger + Untold Works | High | Not Started | Roadmap | Site review complete | Week 2 | DNS update + SSL cert
Register WhatsApp Business | Platform Setup | Roger | High | Not Started | Close | — | Week 1 | ~1 week for Meta approval; critical for Mexico market
Connect WhatsApp Business API to platform | Platform Setup | Untold Works | High | Not Started | Fulfillment | WhatsApp approved | Week 2 | Customer notifications, lead capture, status updates
Roger reviews Master Price List — confirm dealer costs + margins | Catalog & Content | Roger | Critical | Not Started | Close | — | Week 1 | 491 products across 11 brands; need confirmed pricing
Product image audit — flag stock/duplicate photos | Catalog & Content | Untold Works | Critical | In Progress | Close | — | Week 1 | 64 products live, many using stock/duplicate images
Source real product images from manufacturers | Catalog & Content | Roger + Untold Works | Critical | Not Started | Close | Image audit done | Week 2 | Need manufacturer-supplied or real product photography
Replace stock images on 19 brand pages | Catalog & Content | Untold Works | High | Not Started | Close | Real images sourced | Week 3 | Brand pages currently use Unsplash stock photos
Roger walks the site — flag copy/pricing/category issues | Catalog & Content | Roger | Critical | Not Started | Close | — | Week 1 | countercultures.netlify.app/en — full review needed
Copy polish — hero messaging, spec gaps, deduplicate language | Catalog & Content | Untold Works | High | Not Started | Close | Roger's feedback | Week 3 | Hero too generic; 'curated' overused; product specs incomplete
Wire 491 products with confirmed pricing into CRM + site | Catalog & Content | Untold Works | Critical | Not Started | Inventory | Price List confirmed | Week 2 | Master Price List → Google Sheets → Website auto-update
Import 1,019 product images organized by brand/category | Catalog & Content | Untold Works | High | Not Started | Inventory | Images sourced | Week 2 | Google Drive → Website CDN pipeline
First 10 blog posts (bilingual, SEO + AEO) | Catalog & Content | Untold Works | Medium | Not Started | Brand | Site live | Week 5-6 | Brand stories, product guides, project showcases
Sales pipeline operational: leads → quotes → Stripe invoices | Operations Build | Untold Works | Critical | Not Started | Sales | CRM populated + Stripe | Week 3 | Full pipeline: Inquiry → Quoted → Paid → Ordered → Delivered
Finance dashboard — real revenue, margins, payouts | Operations Build | Untold Works | Critical | Not Started | Finance | Stripe + Price List | Week 3 | The big unlock: real-time margin visibility per deal
Order fulfillment pipeline (Ordered → In Transit → Delivered) | Operations Build | Untold Works | High | Not Started | Fulfillment | Pipeline operational | Week 4 | With automated/manual tags per the deck
AI chatbot trained on live catalog | Operations Build | Untold Works | High | Not Started | AI Platform | Products wired | Week 3 | Claude Haiku, bilingual, 24/7, captures contact info
AI dashboard assistant connected to Stripe + CRM | Operations Build | Untold Works | Medium | Not Started | AI Platform | Stripe + CRM live | Week 4 | 'How did we do last month?' → instant answer
Inventory sync system — manufacturer update detection | Operations Build | Untold Works | Medium | Not Started | Inventory | Products wired | Week 5 | AI parses manufacturer updates, flags changes, Roger approves
Automated shipping notifications via WhatsApp | Operations Build | Untold Works | Medium | Not Started | Fulfillment | WhatsApp API + pipeline | Week 5 | Customer gets status updates automatically
Instagram + Facebook connected (Meta Graph API) | Marketing Engine | Untold Works | High | Not Started | Brand | Site live | Week 5 | Free via Meta Graph API; post from dashboard
SEO foundation — meta tags, structured data, sitemap | Marketing Engine | Untold Works | High | In Progress | Discovery | — | Week 5 | Schema.org already in place per site scan
AEO content strategy — AI assistant recommendations | Marketing Engine | Untold Works | Medium | Not Started | Discovery | Blog posts started | Week 6 | Content structured for AI assistants to cite CC
Newsletter capture via Resend | Marketing Engine | Untold Works | Medium | Not Started | Brand | Site live | Week 5 | Free up to 3k/mo; sign-up on site already exists
Trade program accepting applications | Marketing Engine | Untold Works | Medium | Not Started | Discovery | Site live | Week 5 | Architects, designers, contractors; /trade page exists
Social content calendar — first month | Marketing Engine | Untold Works | Medium | Not Started | Brand | Social connected | Week 6 | Product spotlights, project showcases, brand stories
Roger dashboard training session | Launch & Handoff | Untold Works | High | Not Started | Monday Morning | Dashboard built | Week 6 | Walk through the 'Monday Morning' slide scenarios
Finance person training — dashboard + Stripe | Launch & Handoff | Untold Works | High | Not Started | Finance | Finance dashboard live | Week 6 | Manual vs automated responsibilities
Go-live checklist — final pre-launch review | Launch & Handoff | Untold Works | Critical | Not Started | Progress | All ops running | Week 7 | Domain, SSL, redirects, monitoring, backups
7-day post-delivery follow-up automation | Launch & Handoff | Untold Works | Low | Not Started | Fulfillment | WhatsApp + pipeline | Week 8 | Automated customer satisfaction check
Weekly AI-generated business report | Launch & Handoff | Untold Works | Medium | Not Started | Monday Morning | All systems live | Week 8 | Automated Monday morning report: leads, deals, revenue, margin
SEO performance baseline + first month report | Launch & Handoff | Untold Works | Medium | Not Started | Discovery | Site live 4 weeks | Week 8 | Track rankings, traffic, lead sources
Roger confirms delivery timelines by brand/category | Catalog & Content | Roger | Critical | Not Started | Messaging | — | Week 1 | How long from order to delivery? Varies by brand — need ranges for site copy
Roger picks preferred hero headline direction | Catalog & Content | Roger | High | Not Started | Messaging | — | Week 1 | 4 options in Messaging Framework — Direct, Benefit-Led, Story-Led, Simple
Rewrite hero + homepage copy (10-second test) | Catalog & Content | Untold Works | Critical | Not Started | Messaging | Roger picks headline | Week 2 | Current hero 'Smart Bathrooms/Smart Toilets' fails the test completely
Add positioning statements to all 19 brand pages | Catalog & Content | Untold Works | High | Not Started | Messaging | Hero copy approved | Week 3 | 'Counter Cultures is an authorized [Brand] dealer in San Miguel de Allende'
Add delivery/process language to product pages | Catalog & Content | Untold Works | High | Not Started | Messaging | Delivery timelines confirmed | Week 3 | 'Typical delivery: X weeks' + 'We'll quote within 24 hours'
Add footer positioning line (every page) | Catalog & Content | Untold Works | Medium | Not Started | Messaging | Hero copy approved | Week 2 | 'Premium kitchen, bath & hardware — San Miguel de Allende, Mexico'
10-second test audit — every page | Launch & Handoff | Untold Works | High | Not Started | Messaging | All copy updates done | Week 4 | Walk every page: can a stranger tell what CC does in 10 seconds?
Create logo package (full, icon, dark/light, SVG+PNG) | Catalog & Content | Untold Works | Critical | Not Started | Brand | — | Week 1 | All variations needed before any templates can be built
Create brand color + typography reference sheet | Catalog & Content | Untold Works | Critical | Not Started | Brand | — | Week 1 | Dark Botanical palette: hex, RGB, CMYK. Font usage rules.
Create HTML email signatures (Roger + finance) | Catalog & Content | Untold Works | High | Not Started | Brand | Logo package | Week 1 | Logo, name, title, phone, showroom address, social links
Brand Stripe invoice template | Catalog & Content | Untold Works | Critical | Not Started | Finance | Logo package | Week 2 | Every invoice that leaves CC must be branded
Create quote PDF template | Operations Build | Untold Works | Critical | Not Started | Sales | Logo + brand ref | Week 2 | Dashboard generates, saved to Drive, sent to customer
Build welcome email template (Resend) | Operations Build | Untold Works | High | Not Started | Sales | Logo + brand ref | Week 2 | Triggered automatically on new lead
Build order confirmation email template (Resend) | Operations Build | Untold Works | High | Not Started | Fulfillment | Logo + brand ref | Week 2 | Triggered by Stripe payment
Create WhatsApp message templates for Meta approval | Operations Build | Untold Works | High | Not Started | Fulfillment | WhatsApp Business API | Week 2 | Quote ready, order shipped, delivery scheduled — need Meta approval
Build shipping + delivery email templates (Resend) | Operations Build | Untold Works | Medium | Not Started | Fulfillment | Logo + brand ref | Week 3 | Shipping update, delivery confirmation, 7-day follow-up
Create purchase order template for manufacturers | Operations Build | Untold Works | High | Not Started | Fulfillment | Logo + brand ref | Week 3 | Dashboard generates PO, saved to Drive
Create brand guidelines one-pager (PDF) | Catalog & Content | Untold Works | Medium | Not Started | Brand | Logo + color + type ref | Week 2 | Logo usage, colors, fonts, tone. For vendors/partners.
Build newsletter template (Resend) | Marketing Engine | Untold Works | Medium | Not Started | Brand | Logo + brand ref | Week 5 | Monthly/bi-weekly branded email template
Create social media post templates | Marketing Engine | Untold Works | Medium | Not Started | Brand | Logo + brand ref | Week 5 | Instagram + Facebook — product spotlights, project showcases
Build trade welcome kit PDF | Marketing Engine | Untold Works | Medium | Not Started | Discovery | Brand guidelines | Week 6 | How to order, discount structure, brand catalog overview
Create trade price sheets per brand | Marketing Engine | Untold Works | Medium | Not Started | Finance | Master Price List confirmed | Week 6 | Generated from Master Price List with CC branding
Set up Google Drive branded folder structure | Platform Setup | Untold Works | High | Not Started | Brand | Google Workspace connected | Week 2 | Brand Kit, Sales, Finance, Marketing, Customer Docs, Trade, Products, Internal

## Roger's Checklist
Roger's Action Items
Action | Why It Matters | Time Needed | Done?
Walk the live site and flag issues | Copy, pricing, categories, brand descriptions — you know the products better than anyone | 1-2 hours | ☐
Review + confirm the Master Price List | Dealer costs and margins drive the entire finance dashboard. We need accurate numbers. | 2-3 hours | ☐
Provide real product images (or approve manufacturer sources) | Stock photos are killing credibility. 64 products need real shots. | Ongoing | ☐
Share Odoo URL + credentials | We extract your existing customer data, sales history, and invoices | 5 min | ☐
Connect Google Workspace (grant service account access) | Unlocks Drive CRM, email sync, and calendar integration | 10 min | ☐
Confirm phone number + email domain | Currently placeholders on the site. Need the real showroom number. | 5 min | ☐
Register WhatsApp Business account | ~1 week Meta approval. Critical channel for Mexico. | 15 min + wait | ☐
Review site again after we apply your feedback | Second pass to confirm we nailed it before go-live | 1 hour | ☐
Dashboard training session (we'll schedule) | Learn the Monday Morning routine — leads, money, orders, content | 1 hour | ☐
Finance person intro + training | They need to know what's automated vs. what they handle manually | 1 hour | ☐
Confirm delivery timelines by brand/category | People want to know how fast things arrive. We need real numbers for every product page. | 1 hour | ☐
Pick a hero headline direction | 4 options in the Messaging Framework. Which one sounds most like Counter Cultures? | 10 min | ☐

## Monthly Costs
Counter Cultures — Platform Monthly Costs
Service | What It Does | Monthly Cost | Notes
Netlify Pro | Hosting + CDN + SSL | 19 | countercultures.com.mx
Anthropic (Claude Haiku) | AI chatbot + dashboard assistant | 15 | ~$10-20/mo based on usage
Resend | Transactional email + newsletters | 0 | Free up to 3,000 emails/mo
Google Workspace | Drive, Sheets CRM, email, calendar | 0 | Free tier or Roger's existing account
Meta Graph API | Instagram + Facebook posting | 0 | Free
Stripe Mexico | Payment processing | 0 | 3.6% + $3 MXN per transaction (not monthly)
WhatsApp Business API | Customer messaging | 0 | Free for business-initiated; per-conversation after
Domain | countercultures.com.mx | 3 | ~$30-40/year
TOTAL (estimated) |  | 37 | + Stripe transaction fees per deal